GWOMSHAR COMMUNITY INITIATIVE

Empowering communities through sustainable development and youth empowerment

| Education | Health | Development | Youth |
| --- | --- | --- | --- |

5th Street GSS Road  P O 66 Mangu, Plateau State, Nigeria
gwomshar@gmail.com  | +234 705 355 2539

Our Ref: ______________________               Your Ref: _____________________

# GWOMSHAR COMMUNITY INITIATIVE

## COMPREHENSIVE BUSINESS PLAN & PITCH DECK

## EXECUTIVE SUMMARY

### Organization Overview

Gwomshar Community Initiative is a social enterprise dedicated to empowering communities in Plateau State, Nigeria through integrated, sustainable interventions across four critical pillars: quality education, accessible healthcare, community development, and youth entrepreneurship.

### The Opportunity

Plateau State faces critical development challenges:

- Education Gap: Only 52% primary school completion rate; limited vocational skills training

- Healthcare Crisis: Limited healthcare access in rural areas; high maternal and child mortality rates

- Youth Unemployment: 40% youth unemployment creating social instability

- Community Fragmentation: Weak institutional structures limiting coordinated development

### Our Solution

An integrated, community-centered model that addresses root causes—not symptoms—by simultaneously strengthening education, healthcare access, economic opportunity, and community governance.

### The Ask

$50,000-100,000 USD over 18 months to:

- Expand operations from 5 to 15 communities

- Strengthen institutional capacity

- Establish government partnerships for scalable revenue

- Build impact measurement systems

- Create 200+ youth entrepreneurship pathways

### Expected Returns

- Social Impact: 8,000+ direct beneficiaries; 500+ youth entrepreneurs; improved health outcomes

- Financial Sustainability: Move from 30% to 50% earned revenue; achieve breakeven by Year 3

- Model Validation: Proven, scalable model attracting government partnership and replication

### Leadership

- Prof. Zipporah Duguryil Pewat | 20+ years community development experience | Founder & CEO

- Prof. Katniyon Henry David | Education sector expertise | Secretary

- Committed team of 12 professionals across education, healthcare, operations

## SECTION 1: THE PROBLEM & OPPORTUNITY

### 1.1 The Challenge in Plateau State

Demographics & Context:

- Population: ~4.3 million

- 65% living in rural/semi-urban areas with limited services

- High poverty rate: 40% below poverty line

- Vulnerable populations: youth (60% under 25), women (51% of population)

Critical Gaps:

| Challenge | Current Reality | Impact |
| --- | --- | --- |
| Education | 52% primary completion; no vocational skills | Limited economic mobility; youth migration |
| Healthcare | 1 clinic per 10,000 people; high maternal mortality | Preventable deaths; productivity loss |
| Youth Unemployment | 40% unemployment rate; limited entrepreneurship | Social instability; brain drain |
| Community Governance | Weak institutional structures; limited participation | Development delays; inequality perpetuation |

Root Cause Analysis: These challenges are interconnected and systemic:

- Poor education → Limited skills → Unemployment → Poverty → Limited healthcare access → Preventable illness → Reduced productivity → Perpetual poverty cycle

Why Existing Solutions Fall Short:

- Fragmented NGO interventions address single issues without systemic change

- Government programs lack community engagement and sustainability

- Top-down approaches ignore local context and ownership

- Short-term projects leave no lasting institutional capacity

### 1.2 The Market Opportunity

Addressable Market:

- 300,000+ people in rural Plateau State communities without adequate development services

- Government's growing focus on localized development solutions

- Increasing corporate social responsibility budgets seeking authentic partnerships

- Donor community prioritizing integrated, evidence-based interventions

Competitive Advantage: Gwomshar is uniquely positioned because:

- Integrated Approach: Only organization combining education-healthcare-entrepreneurship-governance

- Academic Rigor: University partnership ensures evidence-based, sustainable solutions

- Community Trust: 20+ years relationships in target communities

- Government Readiness: Plateau State actively seeking implementation partners

- Scalable Model: Systematized approach enables replication

## SECTION 2: OUR SOLUTION

### 2.1 Mission, Vision & Core Values

Mission: To empower communities in Plateau State through sustainable interventions in education, healthcare, community development, and youth entrepreneurship, creating pathways for lasting social and economic transformation.

Vision: A thriving community where every individual has access to quality education, healthcare, and economic opportunities to reach their full potential.

Core Values:

- Community-Centered: Community members lead solutions; we facilitate

- Sustainability: Short-term support enabling long-term self-sufficiency

- Equity: Special focus on women, youth, and vulnerable populations

- Evidence-Based: Data-driven decisions with rigorous impact measurement

- Partnership: Collaborative with government, NGOs, communities, private sector

### 2.2 The Integrated Model

Our four-pillar approach creates synergistic impact:

EDUCATION

(Skills & Knowledge)

|

↓

HEALTHCARE

(Healthy Communities)

|

↓

YOUTH ENTREPRENEURSHIP

(Economic Opportunity)

|

↓

COMMUNITY DEVELOPMENT

(Institutional Strength)

PILLAR 1: EDUCATION

- Foundational Skills: Literacy, numeracy, critical thinking for primary & secondary students

- Vocational Training: Practical skills in agriculture, technology, trades, services

- Teacher Development: Capacity building for educators in partner schools

- Outcome: 80%+ of participants advance academically; 70%+ gain employment/entrepreneurship

PILLAR 2: HEALTHCARE

- Health Education: Prevention, nutrition, reproductive health, disease awareness

- Healthcare Access: Partnership with clinics to provide subsidized/free services

- Community Health Workers: Train 2-5 health champions per community

- Outcome: 60%+ reduction in preventable diseases; improved maternal health outcomes

PILLAR 3: YOUTH ENTREPRENEURSHIP

- Business Training: Business planning, financial management, marketing

- Mentorship: Pairing with experienced entrepreneurs

- Micro-Financing: ₦5,000-₦50,000 capital support for startups

- Market Access: Linkage to suppliers, customers, cooperatives

- Outcome: 75%+ successful business launch; average ₦150K annual revenue per entrepreneur

PILLAR 4: COMMUNITY DEVELOPMENT

- Leadership Development: Training community leaders in participatory governance

- Institutional Strengthening: Support community structures, cooperatives, savings groups

- Community Planning: Participatory development planning & implementation

- Outcome: Self-sustaining community institutions managing local development

### 2.3 How It Works

Phase 1: Community Entry & Engagement (Months 1-3)

- Community dialogue & needs assessment

- Leadership engagement & buy-in

- Beneficiary identification & mobilization

- Establish community development committee

Phase 2: Program Implementation (Months 4-12)

- Launch education programs in schools

- Establish health education & clinic partnerships

- Begin youth entrepreneurship training

- Strengthen community institutions

Phase 3: Sustainability & Transition (Months 13-24)

- Scale programs based on success indicators

- Transition to government funding where possible

- Build local institutional capacity for ownership

- Establish community revenue-sharing mechanisms

Phase 4: Scale & Replication (Year 2 onwards)

- Expand to additional communities

- License model to other organizations

- Develop training program for practitioners

### 2.4 What Makes Us Unique

| Aspect | Typical NGO Approach | Gwomshar Approach |
| --- | --- | --- |
| Scope | Single-issue focus (education OR health OR entrepreneurship) | Integrated four-pillar model addressing root causes |
| Sustainability | Project-based; ends when donor funding ends | Built-in revenue model (B2G); designed for long-term |
| Community Role | Beneficiary of services | Co-creator and owner of solutions |
| Evidence | Anecdotal stories | Rigorous impact measurement & data |
| Scale | Limited by grants | Built for government partnership & replication |
| Leadership | Often external consultants | Community-rooted with academic rigor |

## SECTION 3: MARKET ANALYSIS & TRACTION

### 3.1 Market Size & Growth

Total Addressable Market (TAM):

- 300,000+ people in 50+ communities across Plateau State

- Annual development budget allocation: ₦10M+ (government + donors + CSR)

- B2G market: ₦2m+ annual government spend on community development

Serviceable Addressable Market (SAM):

- 50,000 people in 20 communities (realistic 5-year target)

- Accessible through government partnerships & NGO networks

- Market size: ₦20M+ annual opportunity

Serviceable Obtainable Market (SOM):

- Year 1: 2,000 people in 5 communities | ₦20M revenue potential

- Year 3: 8,000 people in 15 communities | ₦75M revenue potential

- Year 5: 20,000 people in 25 communities | ₦150M+ revenue potential

### 3.2 Current Traction (Proof Points)

Education Pillar:

- ✓ Currently serving 300+ students in 5 communities

- ✓ 82% primary school completion rate (vs. 52% state average)

- ✓ 200+ students trained in vocational skills

- ✓ Partnerships with 8 schools in Mangu and Pankshin LGA

Healthcare Pillar:

- ✓ Trained 45 community health workers across 5 communities

- ✓ 3,000+ people accessed subsidized healthcare through partnerships

- ✓ 35% reduction in preventable diseases in pilot communities

- ✓ Partnership with Mangu and Pankshin General Hospitals established

Youth Entrepreneurship Pillar:

- ✓ 120 youth trained in business skills

- ✓ 85 youth entrepreneurs launched businesses

- ✓ ₦8.5M deployed in micro-financing

- ✓ 65% business survival rate (3+ years operating)

Community Development Pillar:

- ✓ 50+ community leaders trained in governance

- ✓ 5 community development structures established

- ✓ ₦15M in community-mobilized development projects

- ✓ Strong government recognition: Letters of commendation from Plateau State Government

### 3.3 Competitive Landscape

Direct Competitors:

- Other NGOs in Plateau State (15-20 active)

- Government community development programs

- International development organizations

Why Gwomshar Wins:

- Integrated Approach: Nobody else doing all four pillars simultaneously

- Government Partnership: Official partnership with Plateau State Government

- Proven Impact: 5+ years of documented results

- Leadership Quality: University-affiliated expertise

- Community Trust: Deep relationships built over decades

- Financial Model: Only one with viable B2G revenue model

### 3.4 Growth Metrics & Key Performance Indicators

| Metric | Year 1 | Year 2 | Year 3 | Target |
| --- | --- | --- | --- | --- |
| Communities Served | 5 | 10 | 15 | 25 |
| Direct Beneficiaries | 2,000 | 5,000 | 8,000 | 20,000 |
| Youth Entrepreneurs | 50 | 150 | 250 | 500 |
| Annual Revenue | $75K | $200K | $500K | $1.5M |
| Earned Revenue % | 30% | 40% | 50% | 60%+ |
| Cost per Beneficiary | $37.50 | $40 | $62.50 | <$100 |

## SECTION 4: BUSINESS MODEL & REVENUE STRATEGY

### 4.1 Revenue Streams

Stream 1: B2G (Government Contracts) - 50% of Revenue by Year 3

- Service: Program delivery for government ministries

- Clients: Plateau State Ministry of Education, Health, Youth Development

- Revenue Model: Annual contracts for program implementation

- Year 1 Target: ₦15M from 2-3 government contracts

- Year 3 Target: ₦50M+ from 5-8 government contracts

Stream 2: Social Enterprise (Training & Services) - 20% of Revenue

- Skills Training Fees: Companies paying for workforce development

- Health Services: Subsidized clinic services with cost-recovery

- Product Sales: Handicrafts, agricultural products from trained groups

- Year 1 Target: ₦8M

- Year 3 Target: ₦20M

Stream 3: Foundation & Donor Grants - 20% of Revenue

- Development Agencies: USAID, GIZ, World Bank-supported programs

- Foundations: Ford Foundation, Comic Relief, Open Society Initiative

- Corporate CSR: Oil companies, banks, multinationals with community focus

- Year 1 Target: ₦10M

- Year 3 Target: ₦15M (declining % as self-sufficiency increases)

Stream 4: Community Contributions - 10% of Revenue

- Cost-Sharing: Communities contributing materials, labor, leadership

- Membership Fees: Community savings groups & cooperatives

- Year 1 Target: ₦2M

- Year 3 Target: ₦10M (builds community ownership)

### 4.2 Unit Economics

Cost Structure per Community per Year:

| Item | Cost | Notes |
| --- | --- | --- |
| Salaries (3 staff) | ₦4.5M | Program officers, admin |
| Education Programs | ₦1.5M | Materials, teacher training |
| Healthcare Initiatives | ₦1.0M | Health worker stipends, materials |
| Youth Entrepreneurship | ₦2.5M | Training, micro-finance administration |
| Community Development | ₦1.0M | Leader training, facilitation |
| Operations (rent, utilities, transport) | ₦2.0M | Office, vehicles, communications |
| Monitoring & Evaluation | ₦0.5M | Data collection, evaluation |
| Total per Community | ₦12.5M | ~$30K USD |

Revenue per Community (Blended):

- Government contract: ₦8M

- Social enterprise: ₦2M

- Grants: ₦2M

- Community contribution: ₦0.5M

- Total: ₦12.5M per community (covering costs + reserves)

Scaling Efficiency:

- Shared management (HQ) covers 25% of salaries across communities

- Bulk purchasing reduces per-unit costs

- Technology automation reduces administrative costs

- Net Result: Cost per beneficiary decreases as we scale

### 4.3 Financial Projections (5-Year)

REVENUE PROJECTIONS

| Year | Government | Social Enterprise | Grants | Community | Total (USD) | Total (₦) |
| --- | --- | --- | --- | --- | --- | --- |
| Year 1 | $12K (30%) | $10K (13%) | $40K (53%) | $2K (4%) | $75K | ₦28.5M |
| Year 2 | $50K (40%) | $25K (15%) | $100K (40%) | $5K (5%) | $200K | ₦76M |
| Year 3 | $150K (50%) | $40K (13%) | $125K (25%) | $10K (12%) | $500K | ₦190M |
| Year 4 | $300K (60%) | $75K (15%) | $100K (20%) | $25K (5%) | $1M | ₦380M |
| Year 5 | $600K (65%) | $150K (16%) | $120K (13%) | $30K (6%) | $1.5M | ₦570M |

EXPENSE PROJECTIONS

| Year | Personnel | Programs | Operations | M&E | Total (USD) |
| --- | --- | --- | --- | --- | --- |
| Year 1 | $30K | $25K | $15K | $5K | $75K |
| Year 2 | $70K | $80K | $35K | $15K | $200K |
| Year 3 | $120K | $250K | $80K | $50K | $500K |
| Year 4 | $180K | $500K | $150K | $80K | $910K |
| Year 5 | $250K | $900K | $250K | $100K | $1.5M |

PROFITABILITY PATHWAY

| Year | Revenue | Expenses | Surplus/Deficit | Status |
| --- | --- | --- | --- | --- |
| Year 1 | $75K | $75K | $0 | Breakeven (with grant support) |
| Year 2 | $200K | $200K | $0 | Breakeven (with grant support) |
| Year 3 | $500K | $500K | $0 | Breakeven with earned revenue only |
| Year 4 | $1M | $910K | $90K | Profitable |
| Year 5 | $1.5M | $1.5M | $0 (with expansion) | Self-Sustaining |

## SECTION 5: IMPLEMENTATION PLAN

### 5.1 Year 1: Foundation & Proof of Concept (0-12 months)

Objectives:

- Expand from 5 to 10 communities

- Achieve 30% earned revenue

- Establish government partnerships

- Build organizational capacity

Milestones:

| Quarter | Key Activities | Targets |
| --- | --- | --- |
| Q1 | Community entry in 5 new communities; hire 8 staff; establish partnerships | 5 communities; 8 staff |
| Q2 | Launch education programs; train 100 youth entrepreneurs; establish government dialogue | 500+ students; 100 youth |
| Q3 | Scale healthcare initiatives; secure first government contract; M&E system setup | 2,000+ people; ₦15M contract |
| Q4 | Impact evaluation; government partnership formalization; Year 2 planning | 2,000 direct beneficiaries |

Budget Allocation for Year 1:

- Personnel (40%): $30K | Management, program officers, admin staff

- Programs (33%): $25K | Education, healthcare, entrepreneurship delivery

- Operations (20%): $15K | Offices, vehicles, communications, materials

- M&E (7%): $5K | Data collection, baseline surveys, reporting

### 5.2 Year 2: Scaling & Sustainability (12-24 months)

Objectives:

- Expand to 15 communities

- Reach 5,000 beneficiaries

- Achieve 40% earned revenue

- Build institutional capacity for scale

Key Initiatives:

- Open 2 regional hubs (East & West Plateau)

- Hire 12 additional staff (total 20)

- Secure 3-4 government contracts

- Launch social enterprise ventures

- Develop training program for practitioners

Year 2 Budget: $200K

- Personnel (35%): $70K

- Programs (40%): $80K

- Operations (17.5%): $35K

- M&E (7.5%): $15K

### 5.3 Year 3: Sustainability & Replication (24-36 months)

Objectives:

- Achieve breakeven with earned revenue

- Expand to 25 communities

- License model to 3-5 organizations

- Establish Gwomshar Institute

Key Initiatives:

- Expand to 2 additional LGAs

- Hire 30+ staff (total 50)

- 5-8 government contracts generating 50% of revenue

- Launch Gwomshar Practitioner Certification Program

- Establish endowment fund

Year 3 Budget: $500K

- Personnel (24%): $120K

- Programs (50%): $250K

- Operations (16%): $80K

- M&E (10%): $50K

### **5.4 Implementation Risks & Mitigation

| Risk | Impact | Mitigation Strategy |
| --- | --- | --- |
| Government delays in contracts | Revenue shortfall | Diversify funding; build grant reserve in Year 1 |
| Community resistance | Program delays | Intensive community engagement; involve leaders early |
| Staff turnover | Capacity loss | Competitive salaries; strong organizational culture |
| Impact measurement challenges | Data gaps | Invest in M&E staff; use proven tools & partners |
| Competitive NGO pressure | Market squeeze | Unique integrated model; differentiation through quality |
| Currency fluctuation (if USD-denominated) | Cost overruns | Use local currency; diversify funding sources |

## SECTION 6: IMPACT MEASUREMENT & OUTCOMES

### 6.1 Impact Framework

Theory of Change: When communities have access to quality education, healthcare, economic opportunity, and strong institutions, individuals break poverty cycles and reach their full potential, creating thriving, self-sustaining communities.

### 6.2 Key Performance Indicators by Pillar

EDUCATION PILLAR

| Indicator | Baseline | Year 1 Target | Year 3 Target |
| --- | --- | --- | --- |
| Students reached | 300 | 800 | 2,500 |
| Primary completion rate | 52% | 70% | 85% |
| Vocational skills trained | 200 | 400 | 1,200 |
| Teacher capacity built | 50 | 100 | 300 |
| Learning outcome improvement | - | +15% | +35% |

HEALTHCARE PILLAR

| Indicator | Baseline | Year 1 Target | Year 3 Target |
| --- | --- | --- | --- |
| People with healthcare access | 3,000 | 5,000 | 12,000 |
| Health workers trained | 45 | 80 | 200 |
| Maternal mortality reduction | - | -20% | -50% |
| Preventable disease reduction | 35% | 45% | 60% |
| Health awareness improvement | - | 60% aware | 85% aware |

YOUTH ENTREPRENEURSHIP PILLAR

| Indicator | Baseline | Year 1 Target | Year 3 Target |
| --- | --- | --- | --- |
| Youth trained | 120 | 250 | 700 |
| Entrepreneurs launched | 85 | 180 | 500 |
| Business survival rate (3+ years) | 65% | 70% | 75% |
| Average entrepreneur income | ₦100K/year | ₦150K/year | ₦250K/year |
| Jobs created | 120 | 300 | 800 |

COMMUNITY DEVELOPMENT PILLAR

| Indicator | Baseline | Year 1 Target | Year 3 Target |
| --- | --- | --- | --- |
| Community leaders trained | 50 | 100 | 250 |
| Institutions strengthened | 5 | 12 | 30 |
| Community projects executed | ₦15M | ₦30M | ₦75M |
| Community revenue generated | - | ₦2M | ₦10M |
| Participation rate (esp. women) | 30% women | 45% women | 60% women |

### 6.3 Measurement Methodology

Data Collection Tools:

- Baseline/Endline Surveys: Quantitative assessment of knowledge, skills, income

- Focus Group Discussions: Qualitative understanding of behavior change

- Community Scorecards: Community-led monitoring of program quality

- Beneficiary Tracking: Longitudinal follow-up of 500 beneficiaries

- Administrative Data: Enrollment, completion, employment data

- Cost-Effectiveness Analysis: Impact per dollar spent

Evaluation Partners:

- Plateau State University (research partnership for rigorous evaluation)

- Independent evaluation firm (Year 3 comprehensive evaluation)

- Community members (participatory evaluation)

### 6.4 Social Return on Investment (SROI)

Conservative Estimate for Year 3:

Inputs: $500K total investment

Outcomes (valued monetarily):

- 2,500 students with improved earning potential: $2.5M (present value)

- 500 entrepreneurs generating ₦250K/year average: $625K additional annual income

- Reduced healthcare costs from prevention: $400K (annual savings)

- Reduced crime/unemployment from youth opportunity: $300K (estimated)

Total Social Value Created: $3.8M+

Social Return on Investment: 7.6:1 (For every $1 invested, $7.60 in social value created)

## SECTION 7: FINANCIAL REQUIREMENTS & USE OF FUNDS

### 7.1 Funding Ask

Total Funding Needed: $50,000 to $100,000 USD over 18 months

### 7.2 Detailed Use of Funds

PERSONNEL (45% - $67,500)

- Program Manager (2 positions): $18,000

- Community Education Officers (4): $16,000

- Health Coordinator: $7,500

- Youth Entrepreneurship Facilitators (3): $15,000

- M&E Officer: $6,000

- Administrative Support: $5,000

- Subtotal: $67,500

PROGRAM DELIVERY (35% - $52,500)

- Education Program Materials & Supplies: $12,000

- Healthcare Partnership & Training: $10,000

- Youth Entrepreneurship Training & Micro-Finance: $20,000

  - Training materials: $5K

  - Micro-finance capital for 100 youth: $15K

- Community Development Facilitation: $10,500

- Subtotal: $52,500

OPERATIONS & INFRASTRUCTURE (15% - $22,500)

- Office Space & Utilities (3 offices): $7,500

- Vehicles & Transportation: $8,000

- Communications & Internet: $3,000

- Equipment & Technology: $2,500

- Insurance & Compliance: $1,500

- Subtotal: $22,500

MONITORING & EVALUATION (5% - $7,500)

- Baseline Survey & Data Collection: $3,000

- M&E Software & Tools: $1,500

- Mid-Term Evaluation: $2,000

- Impact Assessment Training: $1,000

- Subtotal: $7,500

### 7.3 Fund Release Schedule

Tranches (tied to milestones):

| Tranche | Amount | Timeline | Condition |
| --- | --- | --- | --- |
| Tranche 1 | $50K | Immediate (on signing) | Setup phase; staff hiring |
| Tranche 2 | $50K | Month 6 | Achieve 8 communities; 500+ beneficiaries |
| Tranche 3 | $50K | Month 12 | Achieve 10 communities; ₦15M government contract |

### 7.4 Co-Financing Plan

Additional Funding Sources (to reach operational targets):

| Source | Year 1 | Year 2 | Year 3 |
| --- | --- | --- | --- |
| Government Contracts | ₦15M ($36K) | ₦50M ($120K) | ₦150M ($360K) |
| Foundation Grants | ₦25M ($60K) | ₦50M ($120K) | ₦75M ($180K) |
| Social Enterprise | ₦5M ($12K) | ₦15M ($36K) | ₦30M ($72K) |
| Community Contributions | ₦2M ($5K) | ₦5M ($12K) | ₦10M ($24K) |
| THIS GRANT REQUEST | $150K (18 months) | - | - |
| TOTAL AVAILABLE | $263K | $288K | $636K |

## SECTION 8: TEAM & ORGANIZATIONAL CAPACITY

### 8.1 Leadership Team

PROFESSOR ZIPPORAH DUGURYIL PEWAT

- Position: Founder & CEO

- Experience: 20+ years in community development, women's empowerment, educational transformation

- Education: PhD in Education; Masters in Development Studies

- Key Achievements:

  - Designed 5+ community development programs impacting 10,000+ people

  - Published research on community-centered approaches to sustainable development

  - Recognized by Plateau State Government with Community Leadership Award

- Role: Strategic direction, government relations, program design

PROFESSOR KATNIYON HENRY DAVID

- Position: Secretary & Co-Founder

- Experience: 18 years in education sector; university administration

- Education: PhD in Educational Leadership

- Key Achievements:

  - Led curriculum development in 20+ schools

  - Research focus on youth skill development

  - Strong government relationships in education sector

- Role: Education pillar lead, institutional partnerships

DR. LAWRENCE WILFRED (Program Manager, current staff)

- Experience: 8 years community development

- Specialization: Healthcare & community mobilization

- Role: Daily operations, community coordination

### 8.2 Organizational Structure

CEO

(Prof. Pewat)

|

________________|________________

|                |                |

Operations        Programs          M&E

Manager          Director          Officer

|            /  |  \            |

|       Edu  Health Youth     Analytics

|       Coord  Coord  Officer   Team

Admin                |

Finance            Micro-finance

### 8.3 Advisory Board (To Be Established)

- Government Representative (Plateau State Ministry of Education)

- Academic Partner (Plateau State University)

- Private Sector (Successful entrepreneur/CSR leader)

- Community Representative (Community leader from service area)

- International Development Expert (Donor/NGO experience)

Function: Quarterly meetings; strategic guidance; network leverage; accountability

### 8.4 Capacity Building Plan

Year 1 Investments:

- Staff induction & orientation program

- Project management training (PRINCE2/Agile)

- M&E capacity building

- Government relations & contracting

- Financial management & systems

Year 2 Investments:

- Leadership development for senior staff

- Organizational system documentation

- Change management training

- Specialized technical skills (e.g., social enterprise management)

Year 3 Investments:

- Training program development for practitioners

- Certification program creation

- Research & learning focus

- Strategic planning & scaling

## SECTION 9: SUSTAINABILITY & EXIT STRATEGY

### 9.1 Path to Financial Sustainability

Year 1-2: Grant-Dependent Phase

- 50-60% of funding from grants/donors

- Begin building earned revenue (30-40%)

- Establish government partnerships (nascent)

Year 3: Transition Phase

- Reduce grant dependency to 25%

- Grow earned revenue to 50%

- Government contracts contributing 25%

Year 4+: Sustainable Phase

- Grants only 10-15% (for innovation/research)

- Earned revenue 65%+ (government contracts + social enterprise)

- Build endowment fund for shocks/expansion

### 9.2 Long-Term Sustainability Mechanisms

1. Government Partnership Lock-In

- Annual contracts with Plateau State for program delivery

- Proven impact data makes replacement costly for government

- Multi-year MOUs reduce funding uncertainty

2. Social Enterprise Revenue

- Skills training (schools, companies paying for workforce development)

- Health services (clinic partnerships with revenue-sharing)

- Agricultural/craft product sales from trained beneficiaries

- Graduation from grants to earned revenue model

3. Community Ownership

- Community savings groups financing local initiatives

- Community contributions (labor, materials, leadership)

- Community revenue-generating activities

- Reduces dependence on external funding

4. Knowledge Economy

- License integrated model to other NGOs/organizations (₦5M-10M per license)

- Gwomshar Practitioner Certification Program (training fees)

- Research partnerships generating institutional credibility

- Consulting services to government/donors on community development

5. Reserve Fund Strategy

- Build 6-month operating reserve by Year 3

- Emergency fund for revenue shocks (government delays, donor changes)

- Innovation fund for piloting new interventions

- Target: 25% of annual budget in reserves by Year 5

### 9.3 Exit Strategy Options

Option 1: Government Integration (Preferred)

- Timeline: Year 5-7

- Mechanism: Gwomshar becomes official implementation partner for Plateau State Government's community development programs

- Outcome: Stable, long-term government contracts ensure continuity; Gwomshar evolves into semi-autonomous social enterprise

- Precedent: Similar models in Kenya (Equity Bank's Wings to Fly), Rwanda (Government-NGO partnerships)

Option 2: Social Enterprise Spin-Off

- Timeline: Year 4-6

- Mechanism: Profitable social enterprise arms (training, health services, micro-finance) spin off as independent entities

- Outcome: Revenue-generating activities become self-sustaining businesses; Gwomshar retains equity/governance role

- Model: Grameen Bank model of separating social mission from commercial operations

Option 3: Community Ownership Transition

- Timeline: Year 6-8

- Mechanism: Transfer program ownership to strengthened community institutions

- Outcome: Communities fully own and operate programs; Gwomshar provides technical support only

- Success Metric: Communities generating 80%+ of operating budget independently

Option 4: Replication & Licensing

- Timeline: Year 5+

- Mechanism: Package Gwomshar model for replication by other organizations/states

- Outcome: Gwomshar becomes knowledge hub/training institution; earned revenue from licensing

- Impact: Multiplier effect across Nigeria and West Africa

### 9.4 Contingency Planning

Risk Scenario 1: Government Funding Delays

- Mitigation: Maintain 6-month reserve fund; diversify revenue sources; phased program scaling

- Action: Activate bridge financing from foundation partners; reduce expansion until payment received

Risk Scenario 2: Donor Fatigue/Shifting Priorities

- Mitigation: Early transition to earned revenue model; government contracts as anchor

- Action: Accelerate social enterprise development; seek corporate partnerships

Risk Scenario 3: Economic Downturn/Currency Crisis

- Mitigation: Local currency operations; community co-financing; in-kind contributions

- Action: Scale programs based on available resources; focus on highest-impact interventions

Risk Scenario 4: Leadership Transition

- Mitigation: Strong institutional systems; documented processes; leadership pipeline development

- Action: Advisory Board oversight during transition; external management support if needed

## SECTION 10: PARTNERSHIP & COLLABORATION STRATEGY

### 10.1 Current Partnerships

Government Partners

- Plateau State Ministry of Education: School access, teacher training collaboration

- Plateau State Ministry of Health: Healthcare worker training, clinic partnerships

- Plateau State Ministry of Youth Development: Youth entrepreneurship program alignment

- Pankshin Local Government: Community development coordination

- Status: Letters of recognition; informal collaboration; ready for formalization

Academic Partners

- Plateau State University: Research collaboration, impact evaluation, student internships

- Status: Active partnership; joint publications in development

Healthcare Partners

- Pankshin General Hospital: Subsidized healthcare services, health worker training

- Community Health Clinics (5): Referral network, preventive health programs

- Status: Active service delivery partnerships

Community Partners

- Community Development Associations (5): Program co-design, beneficiary mobilization

- Women's Groups (12): Economic empowerment, savings cooperatives

- Youth Forums (8): Entrepreneurship training, mentorship

- Status: Deep trust relationships; active collaboration

### 10.2 Strategic Partnership Priorities (Year 1-3)

Priority 1: Formalize Government Contracts

- Target: Plateau State Ministries (Education, Health, Youth Development)

- Objective: Secure 3-5 annual contracts worth ₦15M-50M total

- Timeline: Q3 Year 1 (first contract); Q4 Year 1-Q2 Year 2 (additional contracts)

- Strategy:

  - Present impact data to government decision-makers

  - Align programs with government priorities

  - Offer cost-effective implementation model

  - Leverage academic credibility

Priority 2: Foundation/Donor Partnerships

- Target: Ford Foundation, Comic Relief, Open Society Initiative, USAID, GIZ

- Objective: Secure $200K-300K in multi-year grants

- Timeline: Ongoing (Year 1-2)

- Strategy:

  - Emphasize integrated model uniqueness

  - Demonstrate community ownership approach

  - Highlight government partnership readiness

  - Present rigorous impact data

Priority 3: Corporate Social Responsibility (CSR)

- Target: Nigerian banks (Access Bank, GTBank), oil companies (Shell, Chevron), multinationals

- Objective: ₦20M-40M annual CSR funding

- Timeline: Year 2-3

- Strategy:

  - Showcase youth entrepreneurship outcomes (workforce development)

  - Offer co-branded programs in target communities

  - Provide measurable impact reporting

  - Create employee volunteer opportunities

Priority 4: Academic/Research Institutions

- Target: Universities (Plateau State, University of Jos), research institutes

- Objective: Joint research, student internships, knowledge production

- Timeline: Year 1-3

- Strategy:

  - Offer field sites for student research

  - Co-publish impact studies

  - Access university resources (expertise, technology)

  - Build credibility through academic validation

Priority 5: NGO/Civil Society Networks

- Target: Plateau State NGO Network, National Community Development Networks

- Objective: Knowledge sharing, joint advocacy, resource mobilization

- Timeline: Year 2-3

- Strategy:

  - Share best practices and lessons learned

  - Coordinate to avoid duplication

  - Joint advocacy for policy change

  - Potential for model licensing/replication

### 10.3 Partnership Value Proposition

What Gwomshar Offers Partners:

To Government:

- Cost-effective program delivery (vs. direct government implementation)

- Community trust and relationships (20+ years)

- Academic rigor and evidence-based approaches

- Measurable impact data for government reporting

- Flexibility and responsiveness

To Donors/Foundations:

- Integrated model addressing root causes (not symptoms)

- Clear path to sustainability (not perpetual dependency)

- Rigorous impact measurement

- Community ownership ensuring lasting change

- Replication potential (scalable model)

To Corporates:

- Authentic community engagement (not superficial CSR)

- Measurable social impact for reporting

- Workforce development pipeline (youth entrepreneurship)

- Positive brand association in communities

- Employee engagement opportunities

To Communities:

- Respectful, participatory approach (not top-down)

- Comprehensive support (not single-issue)

- Long-term commitment (not project-based)

- Capacity building for self-sufficiency

- Evidence-based solutions

## SECTION 11: SCALING & REPLICATION ROADMAP

### 11.1 Three-Phase Scaling Strategy

Phase 1: Proof of Concept (Year 1-2) - CURRENT PHASE

- Geographic Scope: Mangu, Pankshin LGAs (10 communities)

- Beneficiaries: 5,000 direct beneficiaries

- Focus: Model refinement, impact documentation, government partnership

- Success Criteria:

  - 80%+ beneficiary satisfaction

  - Government contract secured

  - Impact data demonstrating effectiveness

  - Operational systems documented

Phase 2: Regional Expansion (Year 3-5)

- Geographic Scope: 3 LGAs in Plateau State (25 communities)

- Beneficiaries: 20,000 direct beneficiaries

- Focus: Geographic expansion, model standardization, social enterprise launch

- Success Criteria:

  - 50% earned revenue achieved

  - 5+ government contracts active

  - Model licensed to 2-3 organizations

  - Breakeven operations

Phase 3: State-Wide Scale & Replication (Year 6-10)

- Geographic Scope: 10+ LGAs in Plateau State; expansion to 2 neighboring states

- Beneficiaries: 100,000+ direct beneficiaries

- Focus: Full state coverage, model replication beyond Plateau, knowledge institution

- Success Criteria:

  - 65%+ earned revenue (fully sustainable)

  - Model replicated in 10+ organizations/locations

  - Gwomshar Institute training 500+ practitioners annually

  - Endowment fund established

### 11.2 Geographic Expansion Priorities

Year 1-2: Consolidation in Pankshin LGA

- Target communities: 5 additional communities (total 10)

- Rationale: Deep roots, existing relationships, government support

- Strategy: Intensive community engagement, model refinement

Year 3-4: Expansion to Adjacent LGAs

- Target LGAs: Mangu, Bokkos (similar demographics, accessible)

- Target communities: 15 new communities (total 25)

- Rationale: Cultural similarity, government interest, road accessibility

- Strategy: Replicate proven model, establish regional hubs

Year 5+: State-Wide Coverage

- Target LGAs: All 17 LGAs in Plateau State (strategic communities in each)

- Target communities: 50+ communities

- Rationale: Full state impact, government partnership depth

- Strategy: Hub-and-spoke model with regional offices

Year 7+: Cross-State Replication

- Target States: Benue, Nasarawa (neighboring states with similar challenges)

- Mechanism: License model to local NGOs; provide technical support

- Strategy: Knowledge transfer, practitioner certification, monitoring support

### 11.3 Replication Model: Gwomshar Institute

Vision: Become the premier training institution for integrated community development in Nigeria

Services:

- Practitioner Certification Program (6-month intensive)

  - Target: NGO staff, government workers, community leaders

  - Curriculum: Integrated model, community engagement, impact measurement

  - Revenue: ₦500K per participant (subsidized for local practitioners)

  - Target: 50 practitioners/year by Year 5

- Model Licensing (for organizations)

  - Target: NGOs, foundations, government agencies

  - Package: Full model documentation, training, ongoing support

  - Revenue: ₦5M-10M per license + annual support fees

  - Target: 5 licenses by Year 5

- Technical Assistance Services

  - Target: Governments, donors, NGOs needing implementation support

  - Services: Program design, M&E systems, community engagement training

  - Revenue: Consulting fees (₦2M-5M per engagement)

  - Target: 10 engagements/year by Year 5

- Research & Knowledge Production

  - Target: Academic institutions, policy makers, development community

  - Products: Publications, case studies, policy briefs

  - Revenue: Research grants, publication fees

  - Impact: Thought leadership, policy influence

### 11.4 Scaling Enablers

Systems & Infrastructure:

- Standard Operating Procedures (SOPs) for all programs

- Digital M&E platform for real-time tracking

- Financial management systems (QuickBooks/Sage)

- HR policies and staff development framework

- Quality assurance protocols

Technology Investments:

- Mobile-based data collection (KoBoToolbox)

- Cloud-based knowledge management system

- Financial tracking software

- Communication platform for distributed teams

- E-learning platform for beneficiary training

Organizational Development:

- Leadership pipeline development

- Performance management system

- Strong organizational culture and values

- Decentralized decision-making structures

- Learning organization mindset

Financial Infrastructure:

- Diversified funding portfolio

- Reserve fund for growth capital

- Credit facility for cash flow management

- Social enterprise entities for revenue generation

- Endowment fund for long-term stability

## SECTION 12: CALL TO ACTION & NEXT STEPS

### 12.1 The Opportunity for Funders

Why Invest in Gwomshar Now?

- Proven Model: 5+ years of documented impact; not an untested theory

- Scaling Ready: Systems, partnerships, and team in place to expand rapidly

- Government Buy-In: Official recognition and partnership readiness with Plateau State

- Path to Sustainability: Clear transition from grants to earned revenue (50% by Year 3)

- Multiplier Effect: Investment enables 3X leverage through government contracts and co-financing

- Unique Approach: Only organization with integrated four-pillar model in Plateau State

- Exceptional ROI: $7.60 social value created per $1 invested (conservative SROI)

- Replication Potential: Model designed for scale across Nigeria and West Africa

What Your Investment Enables:

$50,000 Investment Over 18 Months:

- Expand to 8 communities (from 5)

- Reach 3,500 direct beneficiaries

- Train 150 youth entrepreneurs

- Establish 2 government contracts

- Build M&E systems for impact tracking

$75,000 Investment Over 18 Months:

- Expand to 10 communities

- Reach 5,000 direct beneficiaries

- Train 250 youth entrepreneurs

- Establish 3-4 government contracts

- Launch social enterprise initiatives

- Build organizational capacity for scale

$100,000 Investment Over 18 Months:

- Expand to 12 communities

- Reach 6,000 direct beneficiaries

- Train 300 youth entrepreneurs

- Establish 5 government contracts

- Launch Gwomshar Institute (practitioner training)

- Achieve 40% earned revenue milestone

- Position for full sustainability by Year 3

### 12.2 Investment Terms

Grant Structure: Unrestricted operating support (preferred) or program-designated

Reporting:

- Quarterly financial reports

- Bi-annual narrative impact reports

- Annual comprehensive evaluation

- Real-time dashboard access for key metrics

Site Visits: Funders welcome for community visits (coordinated through Gwomshar)

Recognition:

- Acknowledgment in annual reports and communications

- Co-branding opportunities (if desired)

- Speaking opportunities at events

- Media visibility in success stories

Engagement Options:

- Advisory Board participation (if interested)

- Technical support/expertise sharing

- Networking with other funders/partners

- Joint advocacy for policy change

### 12.3 Due Diligence Package

Available Upon Request:

- ✓ Audited financial statements (last 3 years)

- ✓ Organizational registration documents (CAC, tax clearance)

- ✓ Board resolution approving funding request

- ✓ Letters of recommendation from government partners

- ✓ Academic research validating impact

- ✓ Beneficiary testimonials and case studies

- ✓ Detailed budget breakdown with assumptions

- ✓ Risk assessment matrix

- ✓ Monitoring & Evaluation framework

- ✓ Strategic plan (2025-2030)

### 12.4 Next Steps for Interested Funders

Step 1: Initial Conversation (Week 1)

- 30-minute call with Prof. Zipporah Pewat (CEO)

- Discuss alignment with funder priorities

- Share additional materials as needed

Step 2: Deep Dive (Week 2-3)

- Detailed presentation of model and impact

- Financial review and due diligence

- Site visit to Plateau State (optional but encouraged)

- Reference checks with government/academic partners

Step 3: Proposal Refinement (Week 4)

- Customize investment amount and focus areas

- Align reporting and engagement preferences

- Finalize grant agreement terms

Step 4: Partnership Launch (Week 5-6)

- Sign grant agreement

- Release Tranche 1 funding

- Kick-off meeting with Gwomshar team

- Establish communication and reporting cadence

## SECTION 13: APPENDICES

### Appendix A: Organizational Documents

- Certificate of Incorporation (CAC)

- Tax Clearance Certificate

- Board Composition and Governance Structure

- Annual Reports (2022-2024)

### Appendix B: Impact Evidence

- Baseline and Endline Survey Results (5 communities)

- Academic Research: "Community-Centered Approaches to Sustainable Development in Plateau State" (2023)

- Case Studies: 10 Beneficiary Success Stories

- Government Commendation Letters

### Appendix C: Financial Documentation

- Detailed 5-Year Financial Model (Excel)

- Audited Financial Statements (2022-2024)

- Budget Assumptions and Notes

- Cash Flow Projections

### Appendix D: Program Materials

- Education Curriculum Framework

- Health Worker Training Modules

- Youth Entrepreneurship Training Manual

- Community Development Facilitation Guide

### Appendix E: Partnership Agreements

- MOU Template with Plateau State Government

- Partnership Agreement with Plateau State University

- Community Engagement Protocol

### Appendix F: Contact Information

Gwomshar Community Initiative
Headquarters: Mangu, Plateau State, Nigeria

Prof. Zipporah Duguryil Pewat
Founder & CEO
Email: gwomshar@gmail.com

Phone: +234 705 355 2539

Prof. Katniyon Henry David
Secretary & Co-Founder
Email: gwomshar@gmail.com
Phone: +234 705 355 2539

Website: www.gwomshar.org (under development)
Social Media: [LinkedIn: https://www.linkedin.com/in/gwomshar-gwomshar-187553399/]

## CLOSING STATEMENT

Breaking Cycles, Building Futures

In communities across Plateau State, the cycle of poverty continues—not because people lack potential, but because they lack opportunity. Gwomshar Community Initiative is changing that reality.

We don't just provide education; we create pathways to economic mobility.
We don't just offer healthcare; we build healthy, thriving communities.
We don't just train entrepreneurs; we ignite sustainable economic transformation.
We don't just strengthen institutions; we empower communities to own their future.

Our integrated model works. The data proves it. The communities confirm it. The government recognizes it.

Now we need partners who believe what we believe: that communities—when given the right tools, resources, and support—can break cycles of poverty and build futures of prosperity.

Your investment in Gwomshar isn't charity. It's a strategic bet on a proven model, exceptional leadership, and the boundless potential of Plateau State communities.

Join us. Let's scale impact. Together.

Thank you for considering this investment in transformation.

This pitch deck and business plan was prepared by Gwomshar Community Initiative for prospective funders and partners. All data is accurate as of January 2026. For questions or additional information, please contact Prof. Zipporah Duguryil Pewat at z.pewat@gwomshar.org. gwomshar@gmail.com +234 705 355 2539